## Agile Sprint Backlog
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 6 | DAY 5 | SPRINT REVIEW
User Story #1 | 8
Task |  |  |  | 7 | 5 | 3 | 0 | 0 | 10 | 0 | 0
Task |  |  |  | 3 | 1 | 1 | 5 | 0 | 5 | 1 | 0
Task |  |  |  | 1 | 0.5 | 0 | 3 | 0 | 6 | 0 | 0
Task |  |  |  | 0.5 | 1 | 2 | 3 | 1 | 4 | 0 | 0
User Story #2 | 1
Task |  |  |  | 3 | 3 | 0.5 | 0.5 | 0 |  | 0 | 2
Task |  |  |  | 3 | 5 | 5 | 1 | 1 |  | 1 | 0
Task |  |  |  | 2 | 2 | 5 | 0 | 1 |  | 0 | 1
Task |  |  |  | 5 | 5 | 9 | 5 | 1 |  | 0 | 1
User Story #3 | 5
Task |  |  |  | 8 | 6 | 0 | 0 | 0 |  | 0 | 0
Task |  |  |  | 3 | 1 | 3 | 3 | 3 |  | 0 | 0
Task |  |  |  | 1.5 | 1 | 0.5 | 0.5 | 1 |  | 1 | 0
Task |  |  |  | 2 | 0.5 | 0 | 0 | 0 |  | 0 | 3
User Story #4 | 8
Task |  |  |  | 9 | 4 | 2 | 2 | 1 |  | 1 | 0
Task |  |  |  | 6 | 6 | 3 | 3 | 3 |  | 1 | 1
Task |  |  |  | 6 | 2 | 8 | 8 | 1 |  | 0 | 1
Task |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  | 0 | 0
User Story #5 | 3
Task |  |  |  | 2 | 1 | 1 | 1 | 0.5 |  | 1 | 1
Task |  |  |  | 6 | 6 | 6 | 0.5 | 3 |  | 9 | 0
Task |  |  |  | 9 | 9 | 9 | 4 | 3 |  | 3 | 3
Task |  |  |  | 0.5 | 0.5 | 0.5 | 1 | 0.5 |  | 0 | 1
TOTAL |  |  |  | 78 | 60 | 59 | 41 | 20 | 25 | 18 | 14

## Agile Sprint Backlog - BLANK
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1
Task
Task
Task
Task
User Story #2
Task
Task
Task
Task
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 1
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1
Get Coordinates of Properties | 1 | Colby | Done | 1
Generate Google Maps Locations | 3 | Colby | Done | 3
Grab User's Location | 8 | Colby | Hold | 8
Update Docs | 2 | Larisa | Continue | 2 | 0.5 | 0.25 | 0 | 0 | 0.25 | 0
User Story #2
Create Basic GUI | 5 | Alex |  | 5 | 1 | 0 | 2 | 1 | 1
Task
Task
Task
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL |  |  |  | 19 | 1.5 | 0.25 | 2 | 1 | 1.25 | 0

## Sprint 2
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1
Get Description GUI and Map GUI working together | 6 | Alex/Colby | Continue | 6
Get Format of Campus-Wide Emails | 2 | Larisa | Done | 2 | 0.5 | 0 | 0 | 0 | 1.5 | 0
Testing of Combined GUI | 2 | Alex/Colby | Done | 2 | 0 | 0 | 1 | 1 | 1
Task
User Story #2
Task
Task
Task
Task
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL |  |  |  | 10 | 0.5 | 0 | 1 | 1 | 2.5 | 0

## Sprint 3
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1
Create Campus notifications through GUI | 5 |  | Unassigned | 5
Gmail API to push our formatted campus alerts with map | 5 |  | Unassigned | 5
Provide locations of HUB/HILL as static locations on map | 2 | Colby | Done | 2
Clean Up GUI |  | Alex | Current | 5 | 1 | 1 | 2 | 0 | 1 | 0
User Story #2
Use GUI dropdowns/fill in the blank for email creation |  | Alex/Colby | Current | 7 | 1 | 2 | 3 | 2 | 2 | 0
Junit Testing | 4 | Larisa | Current | 4 | 1 | 2 | 1 | 2 | 1 | 2
Optimize Code | 2 | Larisa | Current | 2 | 0.5 | 1 | 1 | 1 | 1 | 5
Create UML | 1 | Larisa | Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL |  |  |  | 31 | 26.5 | 20.5 | 13.5 | 8.5 | 3.5 | -3.5